## Master Register
ACC-REM-001 — ADR-005 Accounting Architecture Remediation & Evidence Register
Purpose: controlled issue register for systematic remediation and independent evidence-based acceptance against ACC-REG-001 v1.0 and ADR-005 v1.0. Baseline repository: olamoooore/Ace-ERC.
CONTROL NOTE: Observed / Affected Files are the minimum mandatory inspection scope, not a whitelist of files to patch. Engineer must complete dependency tracing across callers, models, migrations, APIs, jobs/listeners/events and tests before implementation. Any additional affected path must be recorded.
Issue ID | Workstream | Capability | Severity | Architecture Requirement | Issue Found | Repository Evidence / Source | Observed / Affected Files | Minimum Dependency Trace | Dependency Trace Status | Engineer Changed Files | Engineer Added / Changed Tests | Required Remediation | Acceptance Evidence | Owner | Target Commit / PR | Engineer Status | Evidence Submitted | Hostile Review | Final Verdict | Reviewer Notes | Last Updated
ACC-RM-001 | Wave A — Accounting Authority | ACC-002 | P0 | Operational domains submit business facts via DomainPostingRequest; Posting Policy Mapper derives authoritative accounting lines. | Operational/domain services construct explicit DR/CR PostingRequestLine[] and therefore own journal recipes outside ACC-002. | PostingRequest.php; PostingRequestLine.php; PostingEngine.php::validateRequest()/resolveLines(); AccountRoleResolver.php; key posting services across AR/AP/OCR/POS/Ecommerce/HRM/FX/Fixed Assets; related posting tests. Validation confirmed operational callers can construct DR/CR lines and supply accountId, with explicit accountId taking priority over central mapping. No DomainPostingRequest, PostingPolicyMapper, posting_profile_code or JournalPostingRequest was found. IntercompanyPostingService exists but no active caller was found. | PostingRequest.php; PostingRequestLine.php; PostingEngine.php; AccountRoleResolver.php; InvoiceService.php; AccountingOriginBillService.php; AccountingOriginInvoiceService.php; BillPaymentService.php; VendorBillService.php; credit/debit-note services; BankReconciliationService.php; FxRevaluationService.php; DepreciationService.php; PaymentRefundService.php; OcrPostingService.php; PosPostingService.php; WebOrderPostingService.php; PayrollJournalService.php; ManualJournalPostingService.php; PaymentTransactionCompletionService.php; IntercompanyPostingService.php; JournalEntry/JournalEntryLine/JournalEntryLink; PostingAuditLog; related routes, migrations and tests. | Trace every PostingRequest/PostingRequestLine caller; manual journals; posting profiles/config; account/tax/control mapping; APIs/controllers/routes; models/migrations/constraints; jobs/listeners/observers/events; permissions/RBAC; frontend triggers; tests; direct DB bypass paths; inactive/dead code and contradictory implementations. Prove whether operational callers can control DR/CR, accountId/accountMappingKey, tax account, journal and posting date, and whether explicit accountId overrides central mapping. | PARTIAL |  |  | Introduce governed DomainPostingRequest + versioned posting_profile_code + central Posting Policy Mapper. Restrict explicit line posting to authorised JournalPostingRequest/manual journal paths. | DTO/API contract; policy schema/versioning; migrated callers; positive posting tests; negative test proving operational caller cannot submit arbitrary GL lines; compatibility/migration evidence. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | Intern Repository Gap Analysis V2 was rejected for evidence completion, but an intern V2.1 is NOT an implementation prerequisite. Core ACC-RM-001 finding remains VALIDATED. Engineer may independently complete the required caller/dependency discovery against the exact implementation branch/SHA before coding and must include the final caller inventory in the evidence pack. Dependency Trace remains PARTIAL until that engineer trace closes: complete PostingRequest/PostingRequestLine caller inventory including PaymentRefundService fallback; distinguish raw GL authority from business-reference-to-GL translation outside ACC-002; analyse fallback accounting-policy divergence; cross-link authorization to ACC-RM-019. | 2026-08-14
ACC-RM-002 | Wave A — Accounting Authority | ACC-002 | P0 | Reversal Engine supports FULL_REVERSAL, PARTIAL_REVERSAL, CORRECT_AND_REPOST and component-aware reversal basis/lineage. | Current reversal is a full mirror reversal by swapping debit/credit across all original lines; component-aware partial reversal contract is not implemented. | backend/app/Accounting/DTOs/ReversalRequest.php; backend/app/Accounting/PostingEngine.php::reverse(); DocumentCorrectionService.php; PaymentCorrectionService.php; InvoiceController.php::reverseJournalEntry(); PaymentRefundService.php; WebOrderPostingService.php; PayrollJournalService.php; OcrPostingService.php; PosPostingService.php; DocumentCorrectionPolicyService.php; correction models/migrations/tests. Review confirmed PostingEngine performs full mirror reversal only. No reversal_mode, reversal components or remaining reversible amount found. PaymentRefundService can track partial refund amounts but the GL reversal still reverses the full original journal. Active invoice reset-to-draft also creates reversal directly outside PostingEngine. | ReversalRequest.php; PostingEngine.php; JournalEntry.php; JournalEntryLink.php; PostingAuditLog.php; Payment.php; BillPayment.php; InvoiceController.php; JournalEntriesController.php; DocumentCorrectionsController.php; PaymentCorrectionsController.php; DocumentCorrectionService.php; PaymentCorrectionService.php; PaymentRefundService.php; AccountingAccessService.php; PaymentController.php; WebOrderPostingService.php; PosPostingService.php; PosSyncService.php; OcrPostingService.php; PayrollJournalService.php; correction/refund/journal-link migrations; PaymentRefundServiceTest.php; AFM001AccountingFailureModelTest.php; AuditFixesTest.php; WS06ChannelRuntimeConvergenceTest.php. | Trace every reversal entry point and direct journal reversal path; full/partial/correct-and-repost behaviour; payment refund amount flow and remaining refundable state; invoice/bill/journal corrections; customer and bill-payment corrections; credit/debit-note correction paths; POS/Offline POS; Ecommerce; OCR; Payroll; manual journals; controllers/routes; permissions/RBAC; models/migrations/constraints; lineage/idempotency controls; tests; inactive/dead code; and contradictory reversal implementations. Prove whether requested partial amounts/components reach the reversal engine and identify any path bypassing PostingEngine::reverse(). | PARTIAL |  |  | Implement reversal_mode, reversal_basis, reversal_components[], deterministic policy-derived components and component_remaining_reversible_amount. | Schema/DTO; component lineage persistence; full/partial/correct-and-repost tests; over-reversal negative tests; balanced-entry proof. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | Intern Repository Gap Analysis V2 was rejected for evidence completion, but an intern V2.1 is NOT an implementation prerequisite. Core ACC-RM-002 finding remains VALIDATED. Engineer may independently complete reversal caller/dependency discovery against the exact implementation branch/SHA before coding and must include the final inventory in the evidence pack. Dependency Trace remains PARTIAL until closed: exact PaymentRefund branches; PaymentCorrection stale reverse signature; BillPayment-to-Payment type incompatibility; multi-payment settlement defect cross-linked ACC-RM-013; POS fail-open GL divergence cross-linked ACC-RM-003; authorization cross-linked ACC-RM-019. | 2026-08-14
ACC-RM-003 | Wave A — Accounting Authority | ACC-002 | P0 | Reversal posting, authoritative ReversalRelationship, component consumption, transition evidence and required outbox record commit or roll back together. | PROVEN P0. PostingEngine::reverse() is atomic only for reversal journal/lines/JournalEntryLink/PostingAuditLog. DocumentCorrectionService mutates document lifecycle and creates DocumentCorrectionLink after that transaction returns; those writes can fail independently after GL reversal. POS/offline refund paths also contain caught GL failures that can allow operational refund state to continue. No first-class ReversalRelationship/component-consumption/outbox authority is demonstrated. | PostingEngine.php::reverse(); DocumentCorrectionService.php; DocumentCorrectionLink model/migrations; PaymentCorrectionService.php; PaymentRefundService.php; PosSyncService.php; WebOrderPostingService.php positive outer-transaction pattern; JournalEntryLink.php; PostingAuditLog.php; reversal/correction tests. | PostingEngine.php; JournalEntry.php; JournalEntryLink.php; PostingAuditLog.php; ReversalRequest.php; DocumentCorrectionService.php; DocumentLifecycleService.php; DocumentVersionLinkService.php; DocumentCorrectionLink.php; DocumentCorrectionsController.php; PaymentCorrectionService.php; PaymentRefundService.php; PaymentCorrectionsController.php; InvoiceController.php; WebOrderPostingService.php; OcrPostingService.php; PosPostingService.php; PosOrderController.php; PosSyncService.php; PayrollJournalService.php; JournalEntryObserver.php; EventManagement outbox code; related correction migrations and reversal/atomicity tests. | Trace reversal transaction end-to-end including journal/ledger/link/audit/event, retry/idempotency, migrations/constraints and failure handling. Prove no authoritative reversal artifact commits alone. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Create one authoritative reversal command transaction that includes reversal journal/lines, ReversalRelationship, component consumption, document/payment lifecycle mutation, correction lineage, audit and required outbox record. Caller-specific side effects must either join the same transaction or use an explicit recoverable saga/state machine. Remove fail-open accounting divergence. | Failure injection after GL reversal, lifecycle mutation, lineage write, audit and outbox; all-or-nothing proof; POS/offline GL failure cannot return operational success; idempotent retry; no orphan reversal/document state; regression for WebOrder outer-transaction pattern. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED P0 at immutable trace baseline 5bb8de27d7c9e47cb312c240dc1119d42fba5a3a. Central journal reversal atomicity is a positive control but does not cover document/payment lineage. Engineer must complete final caller inventory against implementation SHA before EVIDENCE_SUBMITTED. Cross-link ACC-RM-002, 012, 013 and 016. | 2026-08-14
ACC-RM-004 | Wave C — Platform Hardening | ACC-001 | P1 | Accounting-period authority must support legal-entity/accounting-book context where applicable. | VALIDATED. FiscalPeriod authority is tenant-schema scoped but does not carry demonstrated legal_entity_id/entity_book_id while posting and close commands already carry entity/book context. Tenant isolation itself is not the defect; the unresolved design question is the canonical period scope policy and migration/backfill strategy. | FiscalPeriod model/migration; FiscalPeriodsController.php; FiscalPeriodValidator.php; PostingRequest.php; PostingEngine.php; FinancialCloseCycleService.php; CloseCycle.php; entity/book models; MultiEntityIntegrationTest.php. | FiscalPeriod.php; fiscal_periods migration; FiscalPeriodsController.php; FiscalPeriodValidator.php; PostingRequest.php; PostingEngine.php; ManualJournalPostingService.php; OcrPostingService.php; FinancialCloseCycleService.php; CloseCycle.php; Financial Close cycle migrations; LockDate.php; lock-date migrations; company_settings lock-date migration; EnsureAccountingLockManageAccess.php; AccountingAccessService.php; CloseCyclesPage.tsx; closeApi.ts; FiscalPeriodTest.php; MultiEntityIntegrationTest.php; related fiscal-period test documentation. | Trace period creation/lookup/current selection/close/reopen/lock/posting validation/reporting by tenant/entity/book. Confirm approved scoping policy before schema change. | COMPLETE |  |  | Approve one canonical FiscalPeriod scope policy, then migrate schema/lookups/close/posting validation accordingly. Preserve tenant isolation and do not add entity/book fields merely to duplicate an already-authoritative relationship if architecture proves another deterministic scope. | Migration/backfill or deterministic relationship proof; period creation/current lookup/post/close/reopen by entity/book; duplicate-period isolation; cross-entity/book negative tests; legacy compatibility. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED scope defect; tenant isolation itself is not proven defective. Engineer must confirm the approved entity/book period model and migration impact against implementation SHA before changing schema. | 2026-08-14
ACC-RM-005 | Wave C — Platform Hardening | ACC-001 / ACC-011 | P1 | Period/transaction locks must be scoped to the applicable accounting authority context. | PROVEN. LockDate has no demonstrated legal-entity/book scope and lock selection is not entity/book-aware. A separate LockDateOverride request/approval workflow exists, but PostingEngine does not demonstrate consumption of that approved record as execution authority; it instead accepts overrideReason/approvedBy and writes its own override evidence. Frontend exposes override request/history without a corresponding approval action. | LockDate.php and migrations; lock validation/override services/controllers; PostingEngine override validation/logging; FinancialCloseCycleService.php; lockDatesApi.ts; Shared RBAC/approval services; override tests. | tenant lock-date migration; LockDate.php; lock validation/override services; FinancialCloseCycleService.php; posting validators consuming lock state. | Trace all lock types/setters/overrides/reopen/posting validation and entity/book context. Identify intentionally tenant-wide locks and permission/SoD for override. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Define canonical lock scope and one override authority. Entity/book-aware lock evaluation must consume the approved override decision/reference at execution time; PostingEngine must not infer approval from caller-supplied IDs. Align close/reopen and frontend approval workflow; retain explicit tenant-wide locks only where policy defines them. | Entity/book lock isolation; approved override required and consumed by ID/version; unapproved/stale/self-approved override blocked; frontend request→approval→retry flow; close/reopen consistency; audit/SoD evidence. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED at trace baseline 5bb8de27d7c9e47cb312c240dc1119d42fba5a3a. Two override representations currently exist; do not create a third. Cross-link ACC-RM-014/019 and ACC-UI-RM-002. | 2026-08-14
ACC-RM-006 | Wave B — Assurance & Close | ACC-010 | P0 | ACC-010 owns the canonical AccountingFinding Registry consumed by Close, Auditor Workspace and Finance AI. | PROVEN P0 authority duplication. Financial Close persists its own fci_ai_findings/AiFinding lifecycle (OPEN/ACCEPTED/EDITED/DISMISSED/ESCALATED/SUPERSEDED) with independent review/disposition fields; it is not demonstrated to be a rebuildable projection of canonical ACC-010 AccountingFinding. FindingController::store also has a demonstrated service-call contract mismatch on the active route. | FinancialClose AiFinding.php; fci_ai_findings migrations; FindingController.php; finding services; FinancialCloseReadinessService.php; Audit/Finance AI finding models; ACC-010 target contracts; route registrations/tests. | FinancialClose AiFinding.php; fci_ai_findings migrations; FinancialCloseReadinessService.php; finding generation/review services; other assurance/audit/tax finding models. | Find every finding/warning/anomaly/control model/table/API. Trace create/status/risk-accept/resolve authority. Prove FCI finding is projection or migrate to canonical ACC-010 without losing history. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Implement/migrate to canonical ACC-010 AccountingFinding authority. If Financial Close retains a local table, it must be a rebuildable projection with no independent lifecycle/disposition authority. Fix active controller/service contract mismatch and preserve history/audit during migration. | Canonical schema/API and migration mapping; one authoritative disposition path; projection rebuild test if retained; old FCI write path blocked; historical finding lineage preserved; controller/runtime tests. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED P0. Financial Close currently behaves as a finding authority, not a proven projection. Engineer discovery must inventory all finding/anomaly models before migration and preserve history. | 2026-08-14
ACC-RM-007 | Wave B — Assurance & Close | ACC-010 / ACC-011 | P1 | Findings used in period close must carry or deterministically resolve applicable tenant/entity/book/period context. | PROVEN. AiFinding has no demonstrated period_id/book_id and review_id can be null; AccountReview has entity/book but no period. FinancialCloseAiAnalysisService review lookup is not period-scoped and creates review context with hard-coded book_id='book-001'. FinancialCloseReadinessService queries reviews/open findings by tenant/entity without period/book filters, so other-period/book evidence can contaminate close readiness. | AiFinding.php and migrations; AccountReview.php/migrations; FinancialCloseAiAnalysisService.php::ensureReview(); FinancialCloseReadinessService.php; close-cycle/readiness tests. | FinancialClose AiFinding.php; FinancialCloseReadinessService.php; AccountReview model/service; close-cycle queries/tests. | Trace Finding -> review -> period/entity/book relationship and readiness queries. Prove deterministic context with prior-period/different-book tests; avoid duplicate fields if authoritative relationship already guarantees scope. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Bind every close-relevant finding deterministically to tenant/entity/book/period through canonical AccountingFinding context or an authoritative non-null relationship. Remove hard-coded book identity and make readiness queries scope-exact. | Prior-period and different-book findings do not contaminate requested close; null review cannot lose scope; no book-001 hard-code; migration/backfill evidence; query tests across multiple periods/books. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED; prior evidence-gap classification is superseded. Hard-coded book-001 plus period/book-unscoped readiness queries establish a concrete scope defect. | 2026-08-14
ACC-RM-008 | Wave B — Assurance & Close | ACC-010 / ACC-011 | P0 | Mandatory Authority Conjunction: Close may proceed only when all applicable mandatory assurance blockers allow; non-blocking findings may remain. | PROVEN P0 close-control defect. The direct close path re-evaluates FinancialCloseCycleService readiness based on tasks, escalations and signoffs, but open/high-risk assurance findings are not a conjunctive blocker. FinancialCloseReadinessService reports open findings yet its is_ready computation does not require openFindings==0. No separate authoritative risk-acceptance gate is demonstrated in the close execution path. | CloseCycleController.php::close(); FinancialCloseCycleService.php::evaluateReadiness()/closeCycle(); FinancialCloseReadinessService.php; AiFinding disposition services; signoff/escalation/task services; risk-acceptance/RBAC searches; tests. | FinancialCloseCycleService.php; FinancialCloseReadinessService.php; close task/signoff/escalation services; canonical assurance/finding services. | Trace every READY_TO_CLOSE/CLOSED path; readiness snapshots; finding disposition/risk acceptance; signoff; stale-state revalidation; reopen. Blocking assurance must gate; advisory must not automatically block. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Make close readiness consume canonical assurance disposition as a mandatory conjunction: advisory findings may remain, mandatory blockers must be resolved, and risk acceptance must be a distinct authorised decision. Revalidate current assurance state inside close execution. | Mandatory blocker prevents close; advisory does not; approved risk acceptance permits only policy-authorised exception; stale finding/risk state is revalidated; direct close API cannot bypass assurance gate; audit links close decision to evidence. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED P0. Close authority must distinguish advisory findings, mandatory blockers and authorised risk acceptance; generic accepted/dismissed AI state is not sufficient risk-acceptance authority. | 2026-08-14
ACC-RM-009 | Wave B — Assurance & Close | ACC-011 | P0 | Close-cycle state, period lock, lock authority evidence and required events must transition atomically or under an explicit recoverable state machine. | PROVEN P0 atomicity defect. closeCycle() persists cycle close, FiscalPeriod lock, LockDate mutation and audit as separate authoritative writes without one enclosing transaction/recoverable state machine. Reopen likewise mutates FiscalPeriod, LockDate, company settings and audit separately. Failure between writes can leave contradictory close/lock state; no required close-completed transactional outbox event is demonstrated. | FinancialCloseCycleService.php::closeCycle()/reopen; FiscalPeriod.php; LockDate.php; company_settings lock-date logic; close audit code; event/outbox integrations; close/reopen tests. | FinancialCloseCycleService.php; FiscalPeriod.php; LockDate.php; close audit/event/outbox code; close/reopen tests. | Trace close/reopen write sequence, transaction/lock boundaries, audit, outbox/events, retries/concurrency. Test failure after each authoritative write and stale-readiness. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Execute close/reopen under one authoritative DB transaction or explicitly recoverable state machine, with execution-time readiness/permission revalidation and required event/outbox persistence in the same financial truth boundary. | Failure injection after every authoritative write; no cycle/period/LockDate/settings contradiction; concurrent close/reopen conflict tests; stale-readiness rejection; retry/idempotency; close/reopen event atomicity. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED P0. Close and reopen contain multi-write partial-commit paths. Cross-link ACC-RM-012 for transactional publication and ACC-RM-014 for execution authority. | 2026-08-14
ACC-RM-010 | Wave C — Platform Hardening | ACC-002 | P1 | Command results distinguish ACCEPTED/REJECTED/BLOCKED/CONFLICT/FAILED with canonical reason/remediation metadata. | PROVEN. PostingResult exposes success plus free-text error instead of canonical ACCEPTED/REJECTED/BLOCKED/CONFLICT/FAILED semantics. Controllers often map materially different conditions such as already-posted, locked period, self-approval and posting failure to the same HTTP 422 shape, preventing deterministic UI/remediation behavior. | PostingResult.php; PostingEngine.php; JournalEntriesController and other PostingResult consumers; API exception/error mapping; frontend posting/error handling; lock/reversal/posting tests. | PostingResult.php; PostingEngine.php; all PostingResult consumers; controller/API exception mapping; frontend posting-status/error mapping. | Trace every PostingResult consumer; map errors to canonical outcomes/reason codes; preserve compatibility; prove UI/API distinguishes BLOCKED/REJECTED/CONFLICT/FAILED. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Introduce one canonical command-result contract with outcome, reason_code, remediation/action metadata, current state/version where applicable, authority/correlation references and retryability. Map existing callers compatibly; do not rely on free-text parsing. | Period lock→BLOCKED; stale version/concurrent command→CONFLICT; invalid request/state→REJECTED; infrastructure failure→FAILED; success→ACCEPTED; API/HTTP/UI mappings are deterministic and backwards-compatible where required. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED at immutable trace baseline 5bb8de27d7c9e47cb312c240dc1119d42fba5a3a. This contract is an enabling dependency for ACC-RM-016 conflict UX and ACC-UI-RM-002 locked-period remediation. | 2026-08-14
ACC-RM-011 | Wave C — Platform Hardening | ACC-002 | P1 | Journal business, workflow, approval and posting states are distinct state dimensions. | PROVEN. JournalEntry primarily has status=draft¦posted plus correction-oriented lifecycle_status/version flags; no independent business/workflow/approval/posting state dimensions are demonstrated. Manual journal posting can move draft directly to posted once current permission/lock checks pass, with no journal-specific Shared Approval decision consumed. | JournalEntry.php and migrations; ManualJournalPostingService.php; journal controllers/routes; PostingEngine.php; correction lifecycle migrations; Shared Approval integrations/search; journal UI/tests. | JournalEntry.php; journal migrations; PostingEngine.php; journal services/controllers; workflow/approval integrations; tests. | Trace every status/lifecycle_status read/write; enumerate values; map to business/workflow/approval/posting dimensions; identify report/UI/API dependencies before migration. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Define distinct journal business, workflow, approval and posting dimensions or prove an equivalent canonical model. Integrate journal approval with Shared Approval/Workflow and ACC-RM-019; material edits must invalidate/rebind approvals as policy requires. | State migration map and transition matrix; independent approval/posting tests; draft cannot post when approval required; material edit invalidates stale approval; reporting/API/UI compatibility; correction lifecycle remains distinct. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED. Current journal lifecycle fields do not prove independent workflow/approval/posting state. Cross-link ACC-RM-019; do not create an Accounting-local workflow engine. | 2026-08-14
ACC-RM-012 | Wave C — Platform Hardening | ACC-002 / Platform Events | P0 | Required authoritative events use a durable transactional outbox and one authoritative publisher per event. | PROVEN P0 transactional-publication gap. Platform DomainEventDispatcher persists/dispatches outside demonstrated origin-transaction atomicity; EventManagement has a separate durable outbox. Accounting/Invoice posting can commit business/financial state before dispatch, leaving a commit→dispatch loss window. The durable outbox is not demonstrated as the authoritative Accounting publication path; ACC-RM-021 separately governs platform event-authority convergence. | PostingEngine.php; InvoiceService post/dispatch flow; Platform/EventBus/DomainEventDispatcher.php and EventRecord; EventManagement OutboxService/models/migrations/processors; Accounting publishers/listeners; event/outbox tests. | PostingEngine.php; event dispatchers/jobs/listeners; existing outbox/inbox migrations/models/publishers; posting/reversal/close event tests. | Search outbox/inbox/publisher/after-commit/retry mechanisms; trace authoritative events end-to-end. If outbox exists, prove same-transaction persistence; do not create duplicate mechanism. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Use one platform event authority and durable transactional publication mechanism. Required Accounting events/outbox records must persist in the same transaction as financial truth; durable delivery/retry occurs after commit. Converge/reuse existing mechanisms and cross-link ACC-RM-021; do not build a third Accounting outbox. | Failure between financial write and event persistence rolls back or yields explicit recoverable state; same-transaction outbox proof; publisher retry; duplicate consumer idempotency; event ownership/version registry; no commit→dispatch loss window. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED P0. Existing platform outbox/retry assets are positive controls but do not prove atomic Accounting publication. ACC-RM-012 owns origin-transaction publication; ACC-RM-021 owns platform event-authority convergence. | 2026-08-14
ACC-RM-013 | Wave D — Payment Lifecycle | ACC-005A / ACC-005B | P1 | Payment Execution and Accounting Settlement are distinct authorities/lifecycles, including uncertain external outcomes and allocation/unapplied cash. | VALIDATED with positive controls. Payment gateway lifecycle already has retry/duplicate/local-processing hardening, but PaymentTransaction does not demonstrate a persisted SUBMISSION_UNKNOWN state and AR/AP settlement remains tightly coupled to posting/allocation. Concrete correction defects include BillPayment→Payment type incompatibility, stale reversal signature, whole-document paid_amount reset on partial refund, and POS/offline fail-open GL divergence. | PaymentLifecycleHardeningTest.php; PaymentTransaction model/services; InvoiceService::recordPayment(); BillPaymentService.php; PaymentCorrectionService.php; PaymentCorrectionsController.php; PaymentRefundService.php; PosSyncService.php; allocation/reconciliation code. | PaymentLifecycleHardeningTest.php; InvoiceService.php::recordPayment(); BillPaymentService.php; payment gateway services/controllers/models; refund/allocation/reconciliation code. | Trace external execution, webhook/callback, local processing, GL posting, allocation/settlement, unapplied cash/payment-on-account, refund/reversal/reconciliation. Preserve existing hardening; prove UNKNOWN handling where applicable. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Preserve proven gateway hardening while separating external Payment Execution from Accounting Settlement. Add governed UNKNOWN/reconciliation states where applicable; support unapplied/on-account settlement policy; recalculate balances from surviving allocations; make correction/refund and operational/GL outcomes atomic or explicitly recoverable. | Existing gateway retry tests stay green; UNKNOWN execution test; multi-payment partial refund preserves unaffected allocations; BillPayment correction runtime test; POS/offline accounting failure cannot falsely complete operational refund; unapplied cash/payment-on-account and reconciliation evidence. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED with positive controls. Do not rewrite proven PaymentLifecycleHardening behavior; align it to ACC-005A/ACC-005B and correct concrete settlement/correction divergence. | 2026-08-14
ACC-RM-014 | Wave B — Assurance & Close | ACC-011 / Shared RBAC | P0 | Close, lock, reopen, risk acceptance and override authorities use explicit permissions and Segregation of Duties. | PROVEN P0 authorization defect. Financial Close routes are authenticated/tenant-scoped but no close-specific RBAC middleware/policy is demonstrated. Close-cycle signoff accepts a role string from the request and readiness counts Owner/Admin/Manager role strings without a demonstrated authoritative role lookup, creating a role-spoofing path. Finding accept/dismiss paths likewise lack demonstrated action-specific permission enforcement. Broad accounting.settings fallback also exists for reopen. | FinancialCloseServiceProvider routes/middleware; CloseCycleController.php::signoff()/close()/reopen; FinancialCloseCycleService signoff/readiness logic; FindingController/service; AccountingAccess/RBAC permission seeds; lock/reopen/override paths; tests. | FinancialCloseCycleService.php; RBAC permission definitions/seeds; close controllers/policies/middleware; lock/reopen/risk-acceptance services/tests. | Trace close/lock/reopen/signoff/override authorization from API to service; enumerate permissions/roles; test self-approval and broad-role fallback; keep Shared RBAC authoritative. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Replace client-supplied/hard-coded role authority with explicit backend permissions and Shared RBAC/SoD policy for close, signoff, reopen, lock override and risk acceptance. Derive role/permission from authenticated authoritative context and revalidate inside execution. Cross-link ACC-RM-019 for general posting/approval authority. | Ordinary authenticated user cannot spoof Owner/Admin/Manager signoff; role without specific close permission fails; self-signoff/SoD negative tests; reopen/override/risk acceptance require distinct authority; stale permission is revalidated; deep-link/API bypass fails; audit evidence. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | Severity escalated P1→P0 based on validated close-signoff authorization bypass at trace baseline 5bb8de27d7c9e47cb312c240dc1119d42fba5a3a. Client-supplied role labels must never confer close authority. | 2026-08-14
ACC-RM-015 | Wave C — Platform Hardening | ACC-002 / Multi-tenancy | P1 | Posting/reversal idempotency and source tracing must be tenant-safe under the runtime tenancy model. | EVIDENCE GAP — do not overclaim cross-tenant defect. Runtime tenancy positively sets tenant schema/search_path, which may isolate ordinary queries. However JournalEntryLink model includes tenant_id while its original tenant migration does not, and a later migration/backfill path adds/assumes tenant-aware fields/constraints. The authoritative deployment contract—schema isolation only, explicit tenant_id, or both—remains unproven. | JournalEntryLink.php; original tenant migration; later tenant-aware JournalEntryLink migration/backfill command; PostingEngine source/reversal idempotency queries; tenancy middleware/connection/search_path setup; deployment-equivalent tenancy tests. | JournalEntryLink.php; PostingEngine.php; tenancy middleware/connection resolver/global scopes; JournalEntryLink migration/constraints; cross-tenant tests. | Trace actual runtime tenancy before query changes. Prove DB/connection isolation, unique constraints and context binding; test identical source IDs across tenants using deployment-equivalent setup. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Engineer must first document the deployment-equivalent tenancy contract and migration history. Then either rely on proven isolated tenant schemas or enforce explicit tenant context/keys consistently; remove ambiguity between model, migration and uniqueness strategy without adding redundant tenant logic. | Deployment-equivalent test with identical source IDs in two tenants; search_path/connection proof; JournalEntryLink schema after full migrations; unique-constraint behavior; backfill integrity; no cross-tenant collision/leakage. If schema isolation alone is authoritative, document why explicit tenant_id is retained or retired. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | EVIDENCE GAP only. Runtime schema isolation is a positive control; no cross-tenant defect should be claimed without deployment-equivalent proof. Engineer discovery is mandatory before any query/schema change. | 2026-08-14
ACC-RM-016 | Wave C — Platform Hardening | ACC-002 / ACC-005 / Shared Concurrency | P0 | Concurrent Command / Financial Capacity Consumption Protection: every authoritative command that consumes financial or operational capacity must lock/reload the authoritative aggregate and revalidate remaining capacity/invariants at execution time. Competing commands must yield one valid effect or canonical CONFLICT. | PROVEN P0. InvoiceService::recordPayment validates against Invoice balance before its transaction and does not demonstrate a locked reload before consuming that balance; concurrent requests can both pass the same stale capacity check. Customer/Vendor credit-note aggregate caps and SalesOrder partial-invoice quantity consumption likewise lack demonstrated aggregate serialization at the consumption point. Positive control: BillPaymentService uses a DB transaction, Bill::lockForUpdate() and amount revalidation. Remaining evidence gap is caller-matrix completeness/deployed concurrency testing; ordinary edit ETag/version protection is still unproven. | InvoiceService.php::recordPayment(); BillPaymentService.php::recordPayment() positive lock/revalidation control; CustomerCreditNoteService.php; VendorCreditNoteService.php; VendorDebitNoteService.php; SalesOrderService.php::createInvoice(); InvoiceController.php; VendorBillsController.php/VendorBillService.php; PostingEngine.php::reverse(); JournalEntryLink constraints/tests. | Invoice/Bill/Payment/Credit/Debit Note/SalesOrder controllers and services; PostingEngine; aggregate models/migrations; source quantity/allocation fields; versioning fields; frontend edit/post/cancel flows; API error mapping; concurrency/idempotency tests. | Trace every command that consumes remaining amount, quantity, reversible amount or state eligibility. Map read→lock/reload→revalidate→permission/period check→idempotency→transition→accounting effect→audit/outbox→commit. Prove stale edits use version/ETag and high-authority commands serialize aggregate consumption. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Standardise financial command execution: optimistic concurrency for ordinary edits; transactional lock/reload and execution-time invariant revalidation for high-authority/capacity-consuming commands; aggregate-level serialization; canonical CONFLICT with current version/state; idempotent retry; audit/version evidence. Preserve proven BillPayment and duplicate-posting controls rather than replacing them. | Two-user AR over-allocation; concurrent customer/vendor credit/debit cap consumption; cancel-vs-payment; edit-vs-post; concurrent reversal; concurrent SalesOrder partial invoicing; stale edit with prior version/ETag; exactly one valid effect; losing command returns canonical CONFLICT with current state/version; regression proving BillPayment lock/revalidation and existing PostingEngine/JournalEntryLink protections remain effective. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED P0 at immutable main commit 5bb8de27d7c9e47cb312c240dc1119d42fba5a3a. The defect is inconsistent concurrency discipline, not absence of locking everywhere. Document correction/version_number is not optimistic concurrency evidence. Preserve the positive BillPayment lock/revalidation and duplicate-posting controls. Implementation is not accepted until runtime concurrency evidence covers the losing-command CONFLICT path. | 2026-08-14
ACC-RM-017 | Wave C — Platform Hardening | Shared Idempotency / Canonical Creation & Promotion | P0 | Human-Confirmed Source-to-Canonical Creation & Promotion Idempotency: where a source-derived workflow requires review/confirmation, the confirmed source state and stable source/command identity must bind to one canonical creation/promotion result. Replays return the same canonical result; independent duplicates are governed separately. | PROVEN P0 promotion race/authority defect. OcrPromotionController invokes promotion without an explicit reviewed-version/confirmation token. OcrPromotionService accepts NEEDS_REVIEW as eligibility, reads the OcrDocument before the transaction with no demonstrated source row lock or unique OCR-to-canonical destination claim, directly creates a live Bill/Invoice, then marks the OCR record PROMOTED. Two concurrent calls can therefore both pass the precondition and create two canonical documents. NEEDS_REVIEW is not human promotion authority. | OcrPromotionController.php promotion endpoint; OcrPromotionService.php promotion transaction and direct Bill/Invoice creation; OcrDocument status/source identity fields; OCR frontend Direct Post/promotion workflow; canonical Invoice/Bill creation services; source hash/idempotency/external-reference controls; PostingEngine/JournalEntryLink positive downstream controls. | All source→canonical create/promotion commands; OCR review/confirm/promote; Accounting-origin Invoice/Bill; SalesOrder→Invoice; CSV/import creation; POS/Ecommerce/webhook/payment callbacks; shared external-reference/idempotency services; API contracts; frontend confirmation/retry handling; tests. | For each source-to-canonical flow, trace source identity, human-confirmed source version/state where applicable, command/idempotency key, atomic claim, canonical destination linkage, replay outcome, timeout/UNKNOWN recovery and separate semantic duplicate detection. Prove shared platform Idempotency Key and External Reference Mapping authority are consumed rather than rebuilt locally. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Implement human-confirmed promotion: REVIEWED(version N) -> explicit CONFIRM PROMOTION -> server revalidate version/state -> lock/atomically claim source -> invoke canonical Invoice/Bill create command -> persist unique source-to-canonical relationship and result -> mark PROMOTED in the same transaction. Same confirmed command/retry returns the existing result; source changes invalidate confirmation. Do not let OCR confidence or NEEDS_REVIEW grant promotion authority. | Concurrent same-OCR promotion produces exactly one canonical destination and one durable source link; losing/retry call returns existing ACCEPTED result or canonical CONFLICT, never a second document; promotion without explicit confirmation is blocked; edit after review forces reconfirmation; timeout retry recovers original destination; direct table insertion path is removed/bypassed in favour of canonical creation service; full source-to-review-to-confirm-to-canonical lineage is queryable. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED P0 at immutable main commit 5bb8de27d7c9e47cb312c240dc1119d42fba5a3a. Sequential protection from final PROMOTED status is not concurrent idempotency. OCR can extract/classify/map/recommend, but it must never self-promote; explicit human confirmation bound to the reviewed source version is mandatory. | 2026-08-14
ACC-RM-018 | Wave C — Platform Hardening | Shared Import / Staging / Canonical Promotion | P0 | Shared Import Staging, Human Review & Canonical Promotion: import must follow upload/source identity → parse → durable staging → validate/map → human review where required → preview → explicit commit/promotion through canonical domain services. Import must not write directly to live canonical tables during parse/review. | PROVEN P0. Accounting Invoice CSV import performs live operational creation during import: customer/contact/SalesOrder/Invoice and related downstream steps can be created before the complete batch has passed review/commit. Later medical-case/posting/row failure can therefore leave earlier live business artifacts. No general durable Accounting staging boundary is demonstrated. Positive platform pattern: ContactImportStaging persists staged rows and separates staging from commit. | InvoiceController.php::import()/createInvoiceFromData(); MigrationWorkbench.php; migration_jobs/migration_batches/migration_exceptions; ContactMasterService contact import flow; ContactImportBatch.php; ContactImportStaging.php positive durable staging/commit pattern; deprecated ImportController.php; canonical Invoice/Bill creation services; ADR-000 NEG-021 direct-live-import prohibition. | All Accounting/customer/vendor/product/COA/opening-balance/import routes and UI; MigrationWorkbench controllers/routes/tables; durable staged-row models; Contact import staging as positive pattern; domain adapters; canonical Invoice/Bill creation services; file hash/source identity; batch/row idempotency; exception/review/preview/commit flows; tests. | Inventory every import route. Classify STAGED vs DIRECT-LIVE. Trace file identity/hash, batch identity, row identity, mapping/validation, durable staged payload, reviewer decisions, commit eligibility, canonical service use, failure recovery, replay/idempotency and partial-commit behavior. Reuse shared import/migration authority; do not copy domain-local staging engines. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Generalise the existing shared import capability into durable file/batch/row staging with validation/mapping results, review state, preview, exceptions and explicit idempotent commit through canonical domain services. Migrate direct-live Accounting imports to upload -> parse -> stage -> validate/map -> review -> preview -> commit/promote. No parse/review operation may create live canonical business truth. | Invalid/unapproved row never becomes live; staged rows survive process restart; preview equals commit-eligible set; same file and same commit replay are deterministic/idempotent; failure at row N or a downstream side effect leaves a recoverable staged/partial-commit state without hidden live artifacts; canonical Invoice/Bill service is invoked; batch/row/source lineage and reviewer decisions are auditable; Contact staging regression remains green. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED P0 at immutable main commit 5bb8de27d7c9e47cb312c240dc1119d42fba5a3a. This is a platform staging-authority defect, not merely CSV validation. Reuse/generalise ContactImportStaging and shared migration assets; do not create AccountingImportStaging as a parallel local authority. | 2026-08-14
ACC-RM-019 | Wave A — Accounting Authority | ACC-002 / Shared Approval & Workflow / Shared RBAC | P0 | Accounting Transaction Approval Gate & Posting Authorization — built on hardened Shared Platform Approval/Workflow: a transaction may create a GL effect only when its current canonical approval/workflow state and explicit posting authority permit it. Accounting consumes shared approval/workflow/RBAC; it must not implement a parallel local approval authority. | PROVEN P0. GL-affecting commands do not consistently consume an authoritative Accounting approval decision immediately before posting or reversal. Some financial actions remain reachable through broad accounting.write authority. Shared ApprovalRequest is a single-reviewer terminal model with one reviewed_by. ApprovalService positively locks the request, checks expiry, blocks self-approval and checks eligibility, but one successful reviewer sets pending to approved. No first-class Accounting quorum or multi-approver decision ledger is demonstrated, and its entitlement map is POS-oriented. A named WorkflowEngine was not found in the traced repository search; this remains an evidence gap, not proof that no workflow exists. | ApprovalRequest.php; ApprovalService.php::createApprovalRequest()/approveRequest()/userCanApprove(); Accounting routes; AccountingAccessService.php; EnsureAccountingWriteAccess.php; EnsureAccountingPostAccess.php; EnsureAccountingReverseAccess.php; VendorBillsController/VendorBillService; InvoiceController.php; credit/debit-note services/controllers; manual journal posting/reversal paths; permission tests. | All transaction post/release/reverse/correct routes and services; Shared Approval Workflow/Policy state; approval requests/decisions; RBAC permissions; SoD/self-approval rules; override policy; stale-approval handling; frontend eligibility; audit/event evidence; tests. | Trace each GL-affecting command from UI/API through shared approval/workflow and RBAC to canonical posting authority. Prove required approval state, decision version, approver eligibility/quorum/SoD, explicit accounting.post/accounting.reverse permission and transaction-time revalidation. Identify any broad accounting.write or role-name fallback. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Harden Shared Platform Approval/Workflow as the single approval authority, then require Accounting commands to consume its current decision inside the posting transaction. Model approval decisions/quorum explicitly rather than a single reviewed_by terminal flip where policy requires multiple approvers. Bind approval to document version/material fields so material edits invalidate approval. Separate prepare/write, approve, post, reverse, override and close authorities and enforce SoD. | accounting.write without accounting.post cannot create GL effect; unapproved, expired, revoked or stale-version transaction cannot post; self-approval fails; configured quorum cannot be satisfied by one reviewer; ineligible role fails; material edit after approval requires reapproval; reverse requires explicit reverse authority; permitted approved command posts exactly once; audit links transaction/version to approval decisions/quorum and posting/reversal result; existing approval lock/self-approval controls remain green. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED P0 at immutable main commit 5bb8de27d7c9e47cb312c240dc1119d42fba5a3a. Preserve Shared ApprovalService locking, expiry and self-approval controls, but do not treat its current single-reviewer POS-oriented contract as sufficient Accounting approval authority. ACC-RM-014 remains close/lock/reopen/risk-acceptance SoD; ACC-RM-019 governs general transaction approval and posting authority. | 2026-08-14
ACC-RM-020 | Wave B — Assurance & Close | Bank Reconciliation / ACC-011 / Shared Evidence | P0 | Canonical Bank Statement Reconciliation & Match Authority: durable external BankStatement/BankStatementLine evidence must reconcile against canonical bank-ledger entries through one authoritative match lifecycle. Match algorithms suggest; humans/authorised policy confirm. Completion is reviewable, idempotent, concurrency-safe and evidence-preserving. | PROVEN P0 architecture split. Active Bank Reconciliation has no demonstrated canonical durable BankStatement/BankStatementLine source authority; the UI collects statement date/balance and checks GL lines directly. AutoMatchingService acceptMatches creates ReconciliationItem without synchronising JournalEntryLine.reconciliation_id/date, while the primary completion path updates both, creating split reconciled-state semantics. AutoMatch validates bank_account_id against chart_of_accounts while the primary controller uses bank_accounts; it does not bind the selected GL line to the requested bank account and uses JournalEntryLine.transaction_date instead of canonical JournalEntry.entry_date. Statistics contract is incompatible with the current service signature/shape. Draft/save/resume, sequence continuity and governed reopen/supersede are not demonstrated. | BankReconciliationService.php; BankReconciliationController.php; AutoMatchingService.php::acceptMatches()/matching/statistics paths; AutoMatchController.php; BankReconciliation.php; ReconciliationItem.php; bank_reconciliations/reconciliation_items/reconciliation_exceptions migrations; BankReconciliationPage.tsx; reconciliation routes/tests. Positive controls: UNIQUE(reconciliation_items.journal_entry_line_id) and useful exact/fuzzy/confidence matching logic. | BankAccount/GL linkage; BankStatement ingestion/feed/import; BankReconciliation/Item/Match models; AutoMatching; adjustments via PostingEngine; routes/RBAC; frontend reconciliation/history; close-readiness; evidence drill-down; concurrency/idempotency/period tests. | Trace statement ingestion/source identity; draft→match→confirm→complete→reopen/supersede lifecycle; BankAccount vs GL identity; statement/ledger date authority; 1:1, 1:N, N:1 matching; account-scoped validation; concurrency/idempotency; sequence/opening balance continuity; exceptions/adjustments; permissions/SoD; lock/close policy; evidence lineage. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Define the canonical BankStatement/BankStatementLine/ReconciliationMatch architecture before implementation. Preserve existing unique GL-line membership and matching algorithms as controls/suggestion logic, but unify reconciled-state persistence, BankAccount identity and ledger date; require explicit governed match confirmation; add draft/save/resume, account/date validation, 1:1/1:N/N:1 matching with amount conservation, concurrency/idempotency, sequence continuity, immutable completion and authorised reopen/correction/supersede lineage. | Durable statement/source identity and duplicate-import replay; same BankAccount identity across routes/services; parent journal entry date used; draft/save/resume; explicit confirmation of suggestions; account-scoped 1:1/1:N/N:1 matches with amount conservation; concurrent same-match gives one accepted/one CONFLICT; completed reconciliation immutable; authorised reopen/supersede lineage; separate adjust vs complete permissions; exception resolution; statement-to-match-to-GL-to-journal-to-business-source drill-down; failure injection; completion replay returns existing result; close-readiness integration. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED P0; dependency trace remains COMPLETE WITH UNRESOLVED EVIDENCE. Implementation is NOT READY until the reconciliation architecture contract is fixed. Do not repair the current page piecemeal. Preserve UNIQUE journal-entry-line membership and useful exact/fuzzy matching, but make them subordinate to one canonical statement/match lifecycle. Period-lock treatment of reconciliation completion remains a policy dependency, not a separately proven defect. | 2026-08-14
ACC-RM-021 | Wave C — Platform Hardening | Shared Domain Event Bus / Platform Events | P0 | Cross-module business events must use the Shared Platform Domain Event Bus with one authoritative event identity/owner; durable outbox/inbox is a delivery mechanism, not a competing domain-event authority. | PROVEN platform convergence/runtime defects. Shared Platform DomainEventDispatcher and EventManagement durable OutboxService coexist with different authority/delivery semantics. The outbox schema has useful unique idempotency and per-consumer controls, but processAccountingConsumer returns success and accounting_entry_created=true without performing or verifying a canonical Accounting side effect. OutboxEvent and OutboxEventConsumer readyForProcessing scopes call DB::raw without importing the DB facade. EventManagementServiceProvider does not register the visible ProcessOutboxEventsCommand. OutboxService generates a payload-stable idempotency key while OutboxEvent::generateIdempotencyKey includes the current timestamp. Whether an external deployment scheduler independently launches the processor remains an evidence gap. | backend/app/Platform/EventBus/DomainEventDispatcher.php; Platform EventRecord/EventSubscription/dead-letter assets; backend/modules/EventManagement/Services/OutboxService.php; Models/OutboxEvent.php and OutboxEventConsumer.php; outbox migration with UNIQUE idempotency_key and UNIQUE(outbox_event_id, consumer_name); EventManagementServiceProvider.php; ProcessOutboxEventsCommand/job/processor paths; Accounting/event publishers and handlers; tests. | DomainEventDispatcher contracts/models/migrations/subscriptions/dead letters; EventManagement outbox schema/service/jobs/consumers; all accounting/domain event publishers/handlers; Laravel events/listeners; transaction/after-commit behavior; retry/replay; module contracts; tests. | Inventory every event producer, dispatcher, outbox writer, publisher, subscription and consumer. Map event names/versions/owners, transaction boundaries, retries/dead letters/replay and actual side effects. Prove one authority per event and that accounting-consumer success means a real canonical accounting side effect. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Converge cross-module events on the Shared Platform Domain Event Bus as authority and subordinate/bridge durable outbox delivery to it. Preserve the outbox unique idempotency/per-consumer constraints, retry/log/checkpoint assets; fix processor runtime/registration; standardise one stable event/idempotency key contract; replace simulated Accounting success with a canonical subscribed handler that verifies the real side effect or returns failure. Cross-link transactional publication acceptance to ACC-RM-012. | Authoritative event registry/version owner; originating transaction plus event-persistence failure-injection proof; duplicate dispatch/retry yields one consumer effect; stable idempotency key on replay; processor command/job is registered and runnable; readyForProcessing executes without namespace/runtime error; Accounting consumer success is backed by a real canonical accounting result and false accounting_entry_created metadata is impossible; retry/dead-letter/replay works; unique event/consumer constraints are preserved; no competing third event authority. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | VALIDATED at immutable main commit 5bb8de27d7c9e47cb312c240dc1119d42fba5a3a. Positive schema controls do not prove a functioning production event pipeline. Proven: false-success Accounting consumer, broken DB facade references in processing scopes, provider omission of the visible processor command, and conflicting idempotency-key generation. Evidence gap: any external scheduler/bootstrap path not represented in the traced module. Reuse/converge existing platform mechanisms; do not build an Accounting-local outbox. | 2026-08-14
ACC-UI-RM-001 | UI/UX — Accounting Setup | Accounting Domain Onboarding / Shared Onboarding | P1 | Accounting onboarding must be a subscribed/domain-specific surface over the authoritative Shared Platform onboarding/setup state, not an independent completion authority. | AccountingOnboardingPage operates a dedicated accounting onboarding session/step lifecycle and hard-coded setup choices. It is not yet demonstrated that completion is derived from or synchronised with the Shared Platform onboarding authority. | frontend/src/pages/accounting/AccountingOnboardingPage.tsx uses /accounting/onboarding/steps and /accounting/onboarding/sessions APIs; Accounting sidebar exposes a separate Onboarding entry. | AccountingOnboardingPage; accounting onboarding controllers/services/models/routes; Shared Platform onboarding/setup services; tenant/entity setup state; completion/readiness gates; navigation; tests. | Trace source of truth for onboarding steps, completion and go-live. Prove Accounting consumes shared onboarding state and adds accounting-specific requirements only as domain contributions/projections. Identify duplicate sessions/statuses and conflicting completion paths. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Make Shared Platform onboarding authoritative; Accounting contributes accounting-specific setup requirements and renders a contextual view. Remove/bridge duplicate completion authority and ensure go-live/readiness consumes the shared state. | One authoritative onboarding status; Accounting view reflects same completion; completing in one surface updates the other; conflicting completion impossible; entitlement/role/entity tests; audit evidence. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | UI remediation; do not redesign shared onboarding inside Accounting. | 2026-08-14
ACC-UI-RM-002 | UI/UX — Accounting Controls | Locked-Period Override Workflow | P1 | When a transaction is blocked by a locked period, the UI must expose the canonical BLOCKED reason and, only for authorised users/policies, a governed override/change-date/request-approval workflow. A generic error is insufficient. | Journal/posting UI surfaces submit create/post/reverse actions and display generic API errors; a complete permission-aware locked-period resolution/override workflow is not demonstrated. | frontend/src/pages/accounting/JournalEntriesPage.tsx; LockDatesPage.tsx; journalEntriesApi; PostingEngine/FiscalPeriodValidator/LockDate validation and override services. | Journal/Bill/Invoice/OCR posting UIs; lock-date UI; posting outcome mapping; override APIs/policies; Shared Approval/RBAC; audit trail; tests. | Trigger locked-period outcomes across each posting surface. Trace API reason/remediation metadata, authorised override eligibility, approval/SoD, date-change alternative, retry and audit. Prove UI never offers override to an unauthorised user. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Render canonical BLOCKED reason/remediation from ACC-RM-010; add permission/policy-aware actions such as change date, request override/approval or cancel. Keep override authority in shared backend policy, not client logic. | Locked-period post shows explicit reason; unauthorised user sees no override action; authorised override follows approval/SoD and logs reason; changed-date flow succeeds; stale lock state revalidated; UI/API tests. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | Cross-link ACC-RM-004/005/010/014/019; this row is the UX workflow, not the lock authority itself. | 2026-08-14
ACC-UI-RM-003 | UI/UX — AI Digitalization | OCR vs Canonical Document Authority / AI Digitalization UX | P1 | OCR is a source-capture/AI digitalization workflow, not a second Invoice/Bill authority. Users must clearly distinguish captured source documents, review/classification, canonical promotion result and posted accounting document. | Accounting navigation labels OCR as 'OCR Bookkeeping' and existing Vendor Bill/document experiences blur captured OCR artifacts with canonical business documents, creating authority ambiguity. | frontend/src/components/layout/Sidebar.tsx; OCRDocumentsPage.tsx; OCRDocumentReviewPage.tsx; DocumentForm.tsx; VendorBills accounting pages; OCR promotion/posting APIs. | Accounting/Vendor Bill navigation; OCR list/review; upload/classify/confirm/promote/post flows; canonical Bill/Invoice detail; destination lineage; permissions; AI confidence/warnings; tests. | Trace the full user journey source capture→AI extraction/classification→human review→canonical promotion→posting. Identify every screen where OCR artifact and canonical Invoice/Bill are represented together and prove authority/status labels and destination linkage are unambiguous. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Position OCR under Domain AI Digitalization/source capture, with optional OCR operations console. Show source status, review state, confidence, canonical destination and promotion/posting status separately. Canonical Invoice/Bill remains authoritative. | User can identify source vs canonical document; promotion shows destination link; no duplicate editing authority after promotion; failed/review states clear; permissions enforced; UX tests. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | Cross-link ACC-RM-017/018 and OCR PRDs. AI suggestion may assist; human/accounting authority remains explicit. | 2026-08-14
ACC-UI-RM-004 | UI/UX — Permission-Aware Actions | Sensitive Accounting & Close Actions | P1 | Sensitive actions must be rendered from authoritative backend eligibility: permission, role/SoD, approval state, period/lock state and record lifecycle. UI visibility must not imply authority. | Financial Close and accounting action surfaces expose status-based signoff/post/reverse controls, while complete permission/approval-aware action eligibility is not demonstrated. | Financial Close pages; Accounting Journal/Invoice/Bill/Credit/Debit/Reconciliation pages; Sidebar requiredPermission support; backend AccountingAccess/RBAC/approval services. | Every sensitive action button/menu; action-eligibility APIs; Shared RBAC; Shared Approval/Workflow; close/lock/reopen/risk acceptance; frontend state caching; tests. | For each sensitive action, trace visible/enabled state to backend eligibility and execution-time revalidation. Test stale permissions/approval/lock state and self-approval/SoD. Identify actions controlled only by local status checks. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Provide permission/policy-aware action eligibility from backend and render disabled/hidden state with reason where appropriate. Backend remains authoritative and revalidates on execution. | Role without permission cannot see/execute sensitive action; stale permission fails safely; approval/SoD/lock state reflected; deep-link/API bypass still 403/BLOCKED; frontend tests. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | Cross-link ACC-RM-014 and ACC-RM-019. | 2026-08-14
ACC-UI-RM-005 | UI/UX — Evidence & Drill-Down | Accounting Evidence Drill-Down | P0 | Accounting reports and transaction surfaces must preserve canonical evidence references so authorised users can drill report→ledger→journal→origin document/source without manually reconstructing IDs. | General-ledger/report pipelines can retain journal/source references internally, but reporting/API/UI projections strip or fail to expose sufficient authoritative references for end-to-end drill-down. | GeneralLedgerService; FinancialReportController; GeneralLedger/TrialBalance/financial report pages; JournalEntry/JournalEntryLine source references; Shared Related Records Registry Service architecture. | All financial report APIs/pages; ledger/journal detail; source-document links; Related Records Registry/Smart Button services; permission-safe metadata; exports; auditor handoff; tests. | Trace each displayed balance/line to ledger entry, journal and originating canonical document/source. Identify where identifiers/references are stripped. Trace Shared Related Records Registry ownership and heterogeneous resource identity before implementing drill-down. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Preserve canonical resource/evidence references in report DTOs and use Shared Platform Related Records Registry/approved module APIs for permission-safe drill-down. Do not create Accounting-local related-record authority. | Report line→ledger lines→journal→source document/source attachment drill-down; permission denial test; export retains reference metadata where policy permits; no manual free-text ID lookup; related-record tests. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | Shared Related Records Registry is the target architecture; its current Contact-owned/UUID implementation still requires platform hardening and is not accepted as-is. | 2026-08-14
ACC-UI-RM-006 | UI/UX — Auditor Workspace | Auditor Canonical Evidence Linkage | P1 | Auditor queries/findings must attach to canonical permission-safe evidence references, not user-entered source_type/source_id text that may be ambiguous or stale. | Auditor query creation currently allows source_type selection and a free-text Source ID such as 'Invoice #12345'; canonical resource validation/resolution and evidence drill-down are not demonstrated. | frontend/src/pages/auditor/AuditorQueriesPage.tsx; AuditQuery.php; AuditQueryController.php; auditor activity/export APIs. | Auditor query UI/API/model; canonical resource resolver/Related Records Registry; report/journal/document drill-down; evidence attachments; permission/masking; audit trail; tests. | Trace query creation from report/transaction/document context; prove source reference resolves to an existing canonical record with tenant/entity/book and permission scope. Test deleted/superseded/restricted sources and evidence handoff. | COMPLETE WITH UNRESOLVED EVIDENCE |  |  | Replace free-text evidence identity with canonical resource reference/selector or context-launched query creation. Preserve source label for display but store validated resource identity and evidence lineage. | Create query from report line and source record; canonical link opens authorised evidence; invalid/restricted source rejected; superseded source lineage preserved; auditor export includes stable reference metadata; tests. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | Server-side auditor permissions are a positive control; this row concerns evidence identity/linkage. | 2026-08-14
ACC-UI-RM-007 | UI/UX — OCR Accounting Mapping | OCR Hard-Coded GL Account IDs | P0 | OCR review/account assignment must load authoritative tenant/entity/book Chart of Accounts and permitted mapping roles; UI must never encode database primary keys as accounting meaning. | OCR DocumentForm Account selector hard-codes SelectItem values 14, 15 and 16 labelled as 5000/5100/5200. Those IDs are tenant/database-specific and can map to the wrong account or no account. | frontend/src/components/ocr/DocumentForm.tsx hard-codes account IDs 14/15/16; OCRDocumentReviewPage.tsx submits reviewed line_items; OcrPostingService.php consumes line_items[].account_id and passes explicit accountId into PostingEngine. | DocumentForm; OCR review APIs; ChartOfAccounts API; AccountRoleResolver/AccountMappingService; OcrPostingService; PostingEngine; tenant/entity/book scope; permissions; tests. | Trace account options from UI to PostingEngine. Prove selected account exists and is permitted in current tenant/entity/book, and determine whether OCR should select semantic mapping role/account key rather than raw GL ID for operational posting under ACC-RM-001. | COMPLETE |  |  | Remove hard-coded IDs immediately. Populate permitted accounts/mapping roles from authoritative API; validate selection server-side; align operational OCR posting with central posting-policy remediation under ACC-RM-001. | No numeric hard-coded account IDs; tenant A/B receive their own accounts; invalid/cross-entity account rejected; renamed/re-numbered account still resolves correctly; OCR post uses approved mapping contract; UI/API tests. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | Directly validated in current main: DocumentForm.tsx encodes 14/15/16 and OcrPostingService consumes explicit account_id. | 2026-08-14
ACC-UI-RM-008 | UI/UX — Accounting Information Architecture | Credit/Debit Note Discoverability | P1 | Credit Notes and Debit Notes are first-class accounting capabilities and must be discoverable from the Accounting information architecture according to role/entitlement, while still linking contextually from Invoice/Bill records. | Customer Credit Note, Vendor Credit Note and Vendor Debit Note routes/pages are implemented, but the Accounting sidebar does not expose them. Users must know hidden routes or reach them indirectly, so implemented financial correction capability is not discoverable. | frontend/src/App.tsx defines /accounting/customers/credit-notes and related Vendor Credit/Debit Note pages/routes; frontend/src/components/layout/Sidebar.tsx Accounting children include invoices/bills/reconciliation/etc. but omit Credit Notes and Debit Notes. | App.tsx accounting routes; Sidebar.tsx/navigation registry; CustomerCreditNotesPage; VendorCreditNotesPage; VendorDebitNotesPage; invoice/bill contextual components; permissions/entitlements; tests. | Trace every Credit/Debit Note entry point, role/entitlement condition, contextual source link and navigation registry. Confirm whether separate menu items or grouped 'Adjustments/Credit & Debit Notes' best preserves accounting IA without duplicating business objects. | COMPLETE |  |  | Expose the existing canonical capabilities through Accounting navigation/registered information architecture with permission-aware counts/links; retain contextual access from Invoice/Bill detail. Do not create duplicate Credit/Debit Note objects. | Authorised user can discover Customer Credit Notes, Vendor Credit Notes and Vendor Debit Notes from Accounting; unauthorised/disabled capability hidden; contextual links still work; routes resolve canonical existing pages; navigation tests. |  |  | OPEN | NO | NOT REVIEWED | NOT ACCEPTED | Finding directly validated: capability exists in routes/pages but is absent from Accounting sidebar navigation. | 2026-08-14

## Dashboard
ACC-REM-001 Dashboard
Metric | Value | Interpretation
Total Issues | 29 | Controlled remediation items in register
P0 Critical | 16 | Must be independently ACCEPTED before ADR-005 implementation conformance/release acceptance
P1 High | 13 | High-priority conformance/hardening items
Open | 29 | Not yet started
In Progress | 0 | Engineer actively remediating
Evidence Submitted | 0 | Awaiting hostile review
Accepted | 0 | Independently accepted
Rejected | 0 | Returned for remediation
Acceptance % | 0% | Accepted ÷ total issues
Gate | Current Result | Rule
ADR-005 Implementation Conformance / Release Acceptance | BLOCKED | All P0 remediation items must be independently ACCEPTED and no rejected item remains. ADR-005 itself remains the approved architecture baseline.

## Evidence Checklist
Evidence Checklist — Minimum Closure Pack
Evidence Type | Mandatory | Requirement | Submission Format | Acceptance Rule | Applies To | Reviewer Check | Notes
Commit / PR identity | YES | Exact commit SHA and PR/branch used as claimed implementation baseline. | SHA + PR link/number | Must identify immutable code baseline. | All issues | NOT REVIEWED
Changed paths | YES | List every changed production/test/migration file relevant to the remediation. | Repository paths | No unexplained implementation path. | All issues | NOT REVIEWED
Schema / migration | WHEN APPLICABLE | Forward migration, backfill and compatibility/rollback strategy. | Migration path + SQL/schema diff | No destructive/unscoped migration; existing data handled. | Schema issues | NOT REVIEWED
API / DTO contract | WHEN APPLICABLE | New/changed command, event, DTO and reason-code contracts. | Contract + examples | Must match ADR authority boundary and remain deterministic. | Contract issues | NOT REVIEWED
Positive automated tests | YES | Normal success path proving intended behavior. | Test file/method + execution output | Executable; not screenshot-only. | All issues | NOT REVIEWED
Negative automated tests | YES | Prohibited/invalid path must fail with expected canonical outcome/reason. | Test file/method + execution output | At least one meaningful prohibited path per issue. | All issues | NOT REVIEWED
Concurrency / idempotency | WHEN APPLICABLE | Race, retry and duplicate-command behavior. | Automated test + DB/result evidence | No duplicate authoritative effect. | Posting, reversal, close, payment, events | NOT REVIEWED
Failure injection / atomicity | WHEN APPLICABLE | Force failure between authoritative writes and verify all-or-nothing or designed recovery. | Automated test + before/after DB state | No partial authoritative state. | Posting, reversal, close, outbox | NOT REVIEWED
Runtime trace | YES | Representative request/workflow trace including IDs, reason codes and resulting authoritative records. | Sanitised request/response + trace IDs | Must be reproducible from claimed baseline. | All issues | NOT REVIEWED
Audit / event evidence | WHEN APPLICABLE | Audit transition and required authoritative event/outbox evidence. | DB/event IDs + publisher evidence | One authoritative publisher; retry/idempotency proven. | Posting, reversal, close, finding, payment | NOT REVIEWED
Caller / dependency inventory | YES | Engineer-owned repository discovery against exact implementation SHA; all authoritative callers, alternate mutation paths, bypasses, jobs/listeners/imports/integrations and dead/inactive paths classified. | CALLER_REFERENCE_INVENTORY.md + final dispositions | No unexplained caller or bypass remains for the changed authority. | All issues; mandatory before EVIDENCE_SUBMITTED | NOT REVIEWED | Prior reviewer/intern traces are inputs only; engineer owns the final inventory.
Capacity / concurrency control | WHEN APPLICABLE | Execution-time lock/reload/version/invariant revalidation for commands consuming balance, quantity, reversible amount, match capacity or lifecycle eligibility. | Concurrent automated tests + before/after DB state | Exactly one valid effect; competing stale command returns canonical CONFLICT/BLOCKED outcome. | ACC-RM-016 and related payment/reversal/close/reconciliation commands | NOT REVIEWED | Include positive regression for existing correct locking controls.
Source confirmation / promotion idempotency | WHEN APPLICABLE | Human-confirmed reviewed source version, atomic source claim, unique source-to-canonical destination and replay-safe canonical result. | Promotion/retry/concurrency tests + lineage evidence | No self-promotion, no duplicate canonical document, edit-after-review forces reconfirmation. | ACC-RM-017; OCR/source-derived creation | NOT REVIEWED | NEEDS_REVIEW or AI confidence never grants promotion authority.
Import staging / commit evidence | WHEN APPLICABLE | Durable file/batch/row staging, validation/mapping/review/preview state and explicit idempotent commit through canonical domain commands. | Batch/row records + preview/commit tests + restart/retry evidence | Before commit, authoritative live mutations are zero; partial failure is truthful/recoverable. | ACC-RM-018 and domain imports | NOT REVIEWED | Reuse shared staging authority; no domain-local parallel import engine.
Approval / SoD / stale-decision evidence | WHEN APPLICABLE | Authoritative approval decision, approver eligibility/quorum/SoD, document/version binding and execution-time permission revalidation. | Decision records + RBAC matrix + negative tests | Write permission alone cannot post/close/reverse; self-approval and stale approval fail. | ACC-RM-014, ACC-RM-019 and related close/posting commands | NOT REVIEWED | Shared RBAC/Approval remains authority; no Accounting-local substitute.
Reconciliation source / match lifecycle | WHEN APPLICABLE | Durable statement/source identity, one match lifecycle, account/date authority, human confirmation, completion/reopen lineage and concurrency-safe amount conservation. | Statement→match→GL→journal→source evidence + concurrency tests | No split-brain reconciled state; completed reconciliation immutable except governed reopen/supersede. | ACC-RM-020 | NOT REVIEWED | Preserve proven unique GL-line and matching controls.
Event / outbox runtime evidence | WHEN APPLICABLE | Originating transaction and required event record are atomic; processor is registered/runnable; consumer success equals a verified real side effect; retry/idempotency/dead-letter work. | Outbox/event IDs + processor execution + failure-injection tests | No commit→dispatch loss window, false-success consumer or duplicate authoritative event mechanism. | ACC-RM-012 and ACC-RM-021 | NOT REVIEWED | Reuse/converge existing event/outbox assets; do not build a third mechanism.
Evidence drill-down / UI authority | WHEN APPLICABLE | Permission-safe UI proves canonical source/destination/authority references and renders backend eligibility/reason codes without creating a second business authority. | Browser/API trace + source IDs + negative permission tests | UI discoverability and drill-down reach the existing canonical objects; hidden/disabled actions match backend authority. | ACC-UI-RM-001 through ACC-UI-RM-008 | NOT REVIEWED | UI remediation is acceptance evidence where it affects authority, auditability or discoverability.

## Status Guide
Status & Acceptance Guide
Status | Meaning | Set By | Exit Criteria | Allowed Next State | Control Rule
OPEN | Issue confirmed and not yet started. | Reviewer / Lead | Engineer accepts scope and begins implementation. | IN_PROGRESS / DEFERRED | Cannot be marked complete.
IN_PROGRESS | Engineer actively remediating. | Engineer | Required evidence pack complete. | EVIDENCE_SUBMITTED | Implementation claim alone is insufficient.
EVIDENCE_SUBMITTED | Engineer has submitted complete repository evidence. | Engineer | Independent review begins. | HOSTILE_REVIEW | No self-acceptance.
HOSTILE_REVIEW | Independent code/test/evidence verification in progress. | Independent Reviewer | All acceptance criteria verified or a defect identified. | ACCEPTED / REJECTED | Review against exact commit SHA.
REJECTED | Evidence or implementation failed acceptance. | Independent Reviewer | Engineer reopens remediation against reviewer findings. | IN_PROGRESS | Reviewer findings must remain recorded.
ACCEPTED | Requirement independently verified against evidence. | Independent Reviewer | Terminal unless later regression/change. | OPEN only via controlled regression/review | No screenshot/AI claim can set ACCEPTED.
DEFERRED | Explicitly postponed with approved reason and owner. | Architecture Lead / Product Owner | Trigger/date/scope reached. | OPEN | P0 cannot be deferred for ADR-005 implementation conformance/release acceptance without an explicit architecture decision.
DEPENDENCY TRACE STATUS | Meaning
NOT STARTED | Required caller/dependency discovery has not begun. | Engineer / Reviewer | Repository trace begins against exact branch/SHA. | Discovery only | No implementation claim may rely on an untraced path.
IN PROGRESS | Dependency/caller discovery is actively being performed. | Engineer | All required dependency classes are classified. | Discovery; narrow implementation only where trace already proves boundary | New callers found must be added to the inventory, not silently ignored.
PARTIAL | Defect may be validated, but required caller/dependency discovery remains materially incomplete. | Reviewer / Engineer | Engineer completes missing trace and records final dispositions. | Implementation may begin only after the engineer closes the missing trace relevant to the changed path; EVIDENCE_SUBMITTED is prohibited while material trace remains partial. | An intern report is not required; engineer-owned discovery against the implementation SHA is authoritative evidence.
COMPLETE WITH UNRESOLVED EVIDENCE | Required dependency classes have been traced sufficiently to establish the defect/remediation boundary, but explicitly identified evidence remains unresolved. | Reviewer / Engineer | Unresolved items are either resolved by engineer discovery or explicitly proven non-blocking and carried into acceptance evidence. | Controlled implementation permitted; unresolved evidence remains mandatory before acceptance where material. | This state is not ACCEPTED and must not be used to hide an unknown implementation bypass.
COMPLETE | Required caller/dependency classes and contradictory implementations are classified for the claimed baseline. | Engineer / Reviewer | Evidence pack references the completed inventory and exact SHA. | Eligible for EVIDENCE_SUBMITTED after implementation evidence is complete. | Complete trace does not mean remediation is accepted.
BLOCKED | Trace cannot be completed because a required authority, environment, dependency or decision is unavailable. | Engineer / Reviewer | Blocking dependency is resolved or explicit architecture decision is issued. | Implementation must not guess across the blocked authority. | P0 block requires escalation; absence of evidence is not permission to implement assumptions.
ENGINEER DISCOVERY RULE | The engineer is responsible for repository discovery/caller inventory on the exact implementation baseline even when prior reviewer or intern traces exist. | Engineer | Final evidence pack contains immutable SHA, caller/reference inventory and remaining exceptions. | Mandatory for every remediation item | Prior reports accelerate discovery but never replace engineer accountability or independent hostile acceptance.

## Release Review
ACC-REM-001 — Pre-Issue Hostile Review & Release Gate
Review Item | Verdict | Finding / Control | Required Before Issue
Current register scope / evidence basis | PASS | ACC-RM-001–021 plus ACC-UI-RM-001–008 are controlled remediation scope. Proven defects, positive controls and evidence gaps are separated; ADR-005 v1.0 and ACC-REG-001 remain the architecture source of truth. | Do not reopen approved architecture through implementation convenience.
Engineer-owned discovery | PASS | Engineer, not intern report, owns final caller/dependency discovery against the exact implementation branch/SHA. Prior reviewer/intern traces are acceleration evidence only. | Final evidence pack must include immutable SHA and caller/reference inventory with every path disposition.
Dependency trace governance | PASS | PARTIAL and COMPLETE WITH UNRESOLVED EVIDENCE are formally defined. Material PARTIAL trace must be closed by engineer discovery before affected implementation is claimed complete. | EVIDENCE_SUBMITTED is prohibited while a material caller/bypass remains unexplained.
Batch A — Accounting command authority | PASS | Primary implementation cluster: ACC-RM-001, 002, 003, 016 and 019. ACC-RM-010 is an enabling command-outcome contract; ACC-RM-012/021 constraints apply where authoritative events are introduced. | Engineer may discover all rows in parallel, but Batch A architecture changes must be dependency-aware and independently hostile-reviewed.
Batch B — Close / assurance authority | PASS | ACC-RM-004, 005, 006, 007, 008, 009 and 014 form one close-control dependency cluster: scope, finding authority, mandatory blockers, atomic close/reopen and SoD. | Do not fix close atomicity while leaving readiness/signoff authority bypasses intact.
Batch C — Source ingestion / promotion | PASS | ACC-RM-017 and 018 govern human-confirmed source promotion/idempotency and shared staged import. ACC-UI-RM-003/007 are coupled UX/account-mapping controls. | No OCR self-promotion and no domain-local import staging engine.
Batch D — Settlement / reconciliation / evidence | PASS | ACC-RM-013 and 020 plus ACC-UI-RM-005/006 govern payment-settlement alignment, canonical bank-statement reconciliation and end-to-end evidence drill-down. | Preserve proven gateway hardening and existing reconciliation matching/unique-line controls.
Platform event convergence | PASS | ACC-RM-012 owns transactional publication from financial truth; ACC-RM-021 owns one platform event authority and truthful durable consumer processing. | Converge existing mechanisms; do not create an Accounting-local third outbox/event bus.
UI remediation boundary | PASS | ACC-UI-RM-001–008 remain separate UI/UX remediation records. They may be implemented with their governing backend batch but cannot create duplicate business authority. | UI acceptance requires backend authority, permission and evidence linkage to remain canonical.
Evidence closure standard | PASS | Source paths, executable positive/negative tests, runtime results, caller inventory and exact SHA are mandatory; concurrency/atomicity/approval/import/reconciliation/event evidence applies by issue. | Screenshot, narrative report or AI claim alone = NOT ACCEPTED.
Independent acceptance | PASS | Engineer cannot self-accept. Implementation moves EVIDENCE_SUBMITTED → HOSTILE_REVIEW → ACCEPTED/REJECTED only after independent code/test/evidence verification. | Review against the exact claimed implementation SHA.
P0 sequencing | CONDITIONAL PASS | Discovery may proceed across all remediation rows. Implementation must follow dependency-aware batches; later-batch work may not silently redesign Batch A shared authority or bypass an unresolved P0 dependency. | Engineer records dependency conflicts/contradictions before coding across the boundary.
Final issue decision | APPROVE TO ISSUE — ENGINEER DISCOVERY + BATCHED IMPLEMENTATION | ACC-REM-001 is approved as the controlled remediation/evidence register for engineer-owned discovery and phased implementation. This is not implementation acceptance and does not change ADR-005 approval status. | Begin with engineer repository discovery and Batch A; each batch requires independent hostile acceptance.
MANDATORY ENGINEER INSTRUCTIONS | 1. Work from an exact branch and commit SHA. 2. Perform your own caller/dependency discovery; prior traces are not a substitute. 3. Affected files are minimum inspection scope, never a patch whitelist. 4. Record every additional caller/bypass and final disposition. 5. Preserve positive controls and existing proven tests. 6. Do not create duplicate Accounting-local shared services. 7. Complete required positive, negative, concurrency, atomicity and runtime evidence. 8. Do not mark EVIDENCE_SUBMITTED with a material unexplained caller/bypass. 9. ACCEPTED is set only by independent hostile review. | Execution rule | Discovery first within each changed authority; controlled replacement path second; migrate callers; disable bypass; prove old failure path; submit evidence.